## Sheet1
iPRIMED Defect Tracker Template
iPRIMED Education Solutions Pvt Ltd #62B, Majestic Terraces, Second Floor Electronic City, Phase I Bangalore - 560100
ID | Test Env | Status (New / Open / InProgress / Fixed / Closed / Reopen) | Assigned To | REQ# (Sprint Number) | Description | Severity (Critical, Major, Minor, Cosmetic) | Priority (High / Medium / Low) | Developer | Comments | Tested Date | Tested By | Verified By | Verified Date | Defect Type | Technical Analysis
1 | design | Fixed | ck@lululemon.com, ssarahs@luluemon.com | sprint 1 | update the design diagrams due to the added requirements | major | Medium |  | -- | 2023-10-30 | Chaitra,Sharon S |  | 2023-11-04 | non-functional
2 | development | Fixed | gurs@lululemon.com | Sprint 2 | User data not added to the database | major | high |  |  | 2023-11-04 | Gowri Urs |  | 2023-11-09 | functional
3 | development | Fixed | mhr@luluemon.com | Sprint 2 | The returns entity not working | major | Medium |  |  | 2023-11-04 | Monika H R |  | 2023-11-09 | functional
4 | development | Fixed | aa2@lululemon.com | Sprint 2 | The admin entity were ocuring null | major | high |  |  | 2023-11-04 | Apoorva A |  | 2023-11-09 | functional
5 | development | Fixed | ck@lululemon.com | Sprint 2 | The orders exceptions were not validated | major | high |  |  | 2023-11-09 | Chaitra K |  | 2023-11-12 | functional
6 | development | Fixed | ssarahs@luluemon.com | Sprint 2 | The shipping address must accept more than one address | major | high |  |  | 2023-11-09 | Sharon S |  | 2023-11-12 | functional
7 | Testing | Fixed | ck@lululemon.com, ssarahs@luluemon.com,mhr@lululemon,gurs@lululemon,aa2@lululemon.com | sprint 2 | Test cases in alll the table were not satisfied | major | high |  |  | 2023-11-09 | All the team members |  | 2023-11-12 | functional
8 | development | Fixed | mhr@lululemon.com | Sprint 3 | The error occuring during login and registration | Critical | high |  |  | 2023-11-13 | Monika H R |  | 2023-11-17 | functional
9 | Authentication | Fixed | ck@lululemon.com, ssarahs@luluemon.com,mhr@lululemon,gurs@lululemon,aa2@lululemon.com | Sprint 3 | All users need to be authenticated and authorised | Critical | high |  |  | 2023-11-17 | All the team members |  | 2023-11-19 | functional